## EXAMPLE_Construction Timeline
Residential Construction Timeline and Scheduling Template
Project Location |  | Project Manager |  | Start Date
Address |  | Name |  | 2028-01-08 | <--Enter date of Sunday of first week.
INSTRUCTIONS: Use this template to track your project's timeline. Each row represents a task or phase. Adjust start/end dates, assign teams, and note dependencies to keep your build on track. | [6 empty] | 2028-01-08 | [6 empty] | 2028-01-15 | [6 empty] | 2028-01-22 | [6 empty] | 2028-01-29 | [6 empty] | 2028-02-05 | [6 empty] | 2028-02-12 | [6 empty] | 2028-02-19 | [6 empty] | 2028-02-26 | [6 empty] | 2028-03-04 | [6 empty] | 2028-03-11 | [6 empty] | 2028-03-18 | [6 empty] | 2028-03-25 | [6 empty] | 2028-04-01 | [6 empty] | 2028-04-08 | [6 empty] | 2028-04-15 | [6 empty] | 2028-04-22 | [6 empty] | 2028-04-29 | [6 empty] | 2028-05-06 | [6 empty] | 2028-05-13 | [6 empty] | 2028-05-20 | [6 empty] | 2028-05-27 | [6 empty] | 2028-06-03 | [6 empty] | 2028-06-10 | [6 empty] | 2028-06-17 | [6 empty] | 2028-06-24 | [6 empty] | 2028-07-01 | [6 empty] | 2028-07-08 | [6 empty] | 2028-07-15
Phase | Task Description | Start Date | End Date | Assigned To | Dependencies | Notes | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa
Preconstruction | Finalize plans, permits, and estimate | 2025-11-01 | 2025-11-04 | Project Manager | N/A | Notes: Ensure permit approvals are complete
Site Prep | Clear lot and grade site | 2025-11-05 | 2025-11-09 | Site Crew | Preconstruction
Foundation | Pour footings and foundation walls | 2025-11-10 | 2025-11-19 | Concrete Contractor | Site Prep
Framing | Construct framing and roof structure | 2025-11-20 | 2025-12-04 | Framing Crew | Foundation | Notes: Schedule framing inspection
Rough-Ins | Install plumbing, HVAC, and electrical systems | 2025-12-05 | 2025-12-14 | Licensed Trades | Framing | Notes: Stagger trade schedules to reduce overlap
Exterior Work | Install windows, doors, and siding | 2025-12-15 | 2026-01-09 | Exterior Crew | Rough-Ins | Notes: Weather-sensitive
Interior Finishes | Drywall, paint, flooring, cabinetry | 2026-01-10 | 2026-01-24 | Interior Crew | Exterior Work | Notes: Order materials early
Final Inspection | Final walkthrough and building inspection | 2026-01-25 | 2026-01-28 | Inspector | Interior Finishes | Notes: Prepare punch list

## BLANK_Construction Timeline
Residential Construction Timeline and Scheduling Template
Project Location |  | Project Manager |  | Start Date
Address |  | Name |  |  | <--Enter date of Sunday of first week.
INSTRUCTIONS: Use this template to track your project's timeline. Each row represents a task or phase. Adjust start/end dates, assign teams, and note dependencies to keep your build on track. | [6 empty] | 2028-01-05 | [6 empty] | 2028-01-12 | [6 empty] | 2028-01-19 | [6 empty] | 2028-01-26 | [6 empty] | 2028-02-02 | [6 empty] | 2028-02-09 | [6 empty] | 2028-02-16 | [6 empty] | 2028-02-23 | [6 empty] | 2028-03-01 | [6 empty] | 2028-03-08 | [6 empty] | 2028-03-15 | [6 empty] | 2028-03-22 | [6 empty] | 2028-03-29 | [6 empty] | 2028-04-05 | [6 empty] | 2028-04-12 | [6 empty] | 2028-04-19 | [6 empty] | 2028-04-26 | [6 empty] | 2028-05-03 | [6 empty] | 2028-05-10 | [6 empty] | 2028-05-17 | [6 empty] | 2028-05-24 | [6 empty] | 2028-05-31 | [6 empty] | 2028-06-07 | [6 empty] | 2028-06-14 | [6 empty] | 2028-06-21 | [6 empty] | 2028-06-28 | [6 empty] | 2028-07-05 | [6 empty] | 2028-07-12
Phase | Task Description | Start Date | End Date | Assigned To | Dependencies | Notes | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa